## ag-grid
NewCo ID | Franchise / Company Owned | Turnover | Projected Opening Date | First Tamper Check | Verifone Device Shipped Date | Verifone Device Delivered Date | Franchisee/Operator | Address | City | State | Zip Code | Coach | Shop Hours
IL0802 | Company Owned | 2026-10-13 | 2026-10-15 | Completed | 09/04/2026 | 09/08/2026 | Caleb Ball, Ryn Burt | 550 W Maple St | New Lenox | IL | 60451 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
VA0101 | Company Owned | 2026-09-25 | 2026-10-16 | Completed | 09/29/2026 | 09/30/2026 | Savannah Cass | 796 Lynnhaven Pkwy | Virginia Beach | VA | 23452 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL2501 | Company Owned | 2026-10-08 | 2026-10-19 | No Devices | Not Shipped | Not Delivered | Sara Rateliff, Bailee Roles | 2906 Halifax Crossing Blvd | Deltona | FL | 32725 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
UT0805 | Company Owned | 2026-10-09 | 2026-10-19 | Seal Verification | 10/08/2026 | 10/09/2026 | Jeremy Munoz | 175 W 1200 S | Logan | UT | 84321 | Christopher Triglia | Sun-Sat: 05am-11pm
WA1608 | Franchise | 2026-10-16 | 2026-10-19 | Pending | 09/15/2026 | 09/16/2026 | Kenneth Stromer | 8704 NE Saint Johns Rd | Vancouver | WA | 98665 | Nate Hartwig | Sun-Sat: 05am-11pm
FL1703 | Company Owned | 2026-10-16 | 2026-10-21 | Seal Verification | 09/17/2026 | 09/18/2026 | Beau Beesley | 4721 Mobile Hwy | Pensacola | FL | 32506 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AZ0703 | Company Owned | 2026-10-16 | 2026-10-23 | No Devices | Not Shipped | Not Delivered | Marly Maxwell | 2469 W Hunt Hwy | San Tan Valley | AZ | 85142 | Krystal Jackson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL1701 | Company Owned | 2026-10-15 | 2026-10-23 | Seal Verification | 09/21/2026 | 09/23/2026 | Andrew Burt, Dominique Girodo | 1616 N. State Route 50 | Bourbonnais | IL | 60914 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL1302 | Company Owned | 2026-10-16 | 2026-10-24 | No Devices | Not Shipped | Not Delivered | Vanessa Huber | 3624 N University St | Peoria | IL | 61604 | Austin Winegar | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0104 | Company Owned | 2026-10-14 | 2026-10-25 | No Devices | Not Shipped | Not Delivered | Kaden Caldwell | 1360 SR-125 | Amelia | OH | 45102 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IN0202 | Company Owned | 2026-10-16 | 2026-10-26 | No Devices | Not Shipped | Not Delivered | Bailey Tollefson | 2110 State St | New Albany | IN | 47150 | Austin Winegar | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TX2005 | Company Owned | 2026-10-21 | 2026-10-29 | No Devices | Not Shipped | Not Delivered | Kristin Leddige | 1261 Kingwood Drive | Kingwood | TX | 77339 | Amanda Bigam | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AZ0104 | Company Owned | 2026-10-16 | 2026-10-30 | No Devices | Not Shipped | Not Delivered | Trevor Jones | 211 George Rothrock Rd | Camp Verde | AZ | 86322 | Michael Coste | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AZ0906 | Company Owned | 2026-10-23 | 2026-10-30 | No Devices | Not Shipped | Not Delivered | Isaac Tully | 170 S Houghton Rd | Tucson | AZ | 85748 | Krystal Jackson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA7504 | Company Owned | 2026-10-23 | 2026-10-30 | No Devices | Not Shipped | Not Delivered | Cameron Brown | 5526 Philadelphia St | Chino | CA | 91710 | Sidney Krall | Sun-Sat: 05am-11pm
OH0606 | Company Owned | 2026-10-20 | 2026-11-02 | No Devices | Not Shipped | Not Delivered | Andre Kane | 5344 W Broad St | Columbus | OH | 43228 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
GA0104 | Company Owned | 2026-10-16 | 2026-11-03 | No Devices | Not Shipped | Not Delivered | Katy Hinton | 4976 Lanier Islands Pkwy | Buford | GA | 30518 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0503 | Company Owned | 2026-10-28 | 2026-11-04 | No Devices | Not Shipped | Not Delivered | Camille Gibassier | 3945 Atlanta Hwy | Montgomery | AL | 36109 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IN0109 | Company Owned | 2026-10-28 | 2026-11-05 | No Devices | Not Shipped | Not Delivered | Dylan Bash | 583 S 3rd St. | Terre Haute | IN | 47807 | Austin Winegar | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA2909 | Franchise | 2026-10-27 | 2026-11-06 | No Devices | Not Shipped | Not Delivered | Kayleigh Slover | 97 Sunset Center | Suisun City | CA | 94585 | Charles Swindler
IN0706 | Company Owned | 2026-10-30 | 2026-11-06 | No Devices | Not Shipped | Not Delivered | César Godoy | 11104 96th place | St John | IN | 46373 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TX5302 | Company Owned | 2026-10-30 | 2026-11-06 | No Devices | Not Shipped | Not Delivered | Morgan Buchanan, Campbell Detwiler | 9937 S Post Oak Rd | Houston | TX | 77096 | Amanda Bigam | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0304 | Company Owned | 2026-11-02 | 2026-11-09 | No Devices | Not Shipped | Not Delivered | Isaac Schoephoerster | 698 Hanes Mall Boulevard, Suite 110 | Winston-Salem | NC | 27103 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL0805 | Company Owned | 2026-11-03 | 2026-11-11 | No Devices | Not Shipped | Not Delivered | Tyler Forman | 764 W Granada Blvd, Unit 2 | Ormond Beach | FL | 32174 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL0702 | Company Owned | 2026-11-05 | 2026-11-11 | Seal Verification | 10/09/2026 | Not Delivered | Whitney Nelson-Vasquez | 4835 W 111th St | Alsip | IL | 60803 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
VA0501 | Company Owned | 2026-11-04 | 2026-11-15 | No Devices | Not Shipped | Not Delivered | Maya Garcia | 21287 Timberlake Rd | Lynchburg | VA | 24502 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
MO1201 | Company Owned | 2026-11-09 | 2026-11-16 | No Devices | Not Shipped | Not Delivered | Stephanie Cotton | 2720 W Broadway Blvd | Sedalia | MO | 65301 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
UT0505 | Company Owned | 2026-10-30 | 2026-11-16 | No Devices | Not Shipped | Not Delivered | Michael Rozsa, Jess McKinstry | 4886 Desert Color Pkwy | St. George | UT | 84790 | Christopher Triglia | Sun-Sat: 05am-11pm
FL1603 | Company Owned | 2026-11-11 | 2026-11-17 | No Devices | Not Shipped | Not Delivered | Ray Haener | 1507 E Fowler Ave | Tampa | FL | 33612 | Shawn McElroy | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL1407 | Company Owned | 2026-11-10 | 2026-11-18 | No Devices | Not Shipped | Not Delivered | Lauren Arant | 7970 Normandy Blvd | Jacksonville | FL | 32221 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
MO0705 | Company Owned | 2026-11-11 | 2026-11-18 | No Devices | Not Shipped | Not Delivered | Tim Roberts | 1816 W Waverly St | Ozark | MO | 65721 | Jayson Jones | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL1004 | Company Owned | 2026-11-11 | 2026-11-19 | No Devices | Not Shipped | Not Delivered | Jessica Lockhart | 14355 Beach Blvd | Jacksonville | FL | 32250 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AZ0527 | Franchise | 2026-11-13 | 2026-11-20 | No Devices | Not Shipped | Not Delivered | Loren Franklin, Caleb Berkey | 1350 N. 43rd Avenue | Phoenix | AZ | 85009 | Charles Swindler
CA7603 | Company Owned | 2026-11-11 | 2026-11-20 | No Devices | Not Shipped | Not Delivered | Brady Benner | 20377 Avalon Blvd | Carson | CA | 90746 | Sidney Krall | Sun-Sat: 05am-11pm
FL3702 | Company Owned | 2026-11-12 | 2026-11-20 | No Devices | Not Shipped | Not Delivered | Zachary Megale | 7215 Lawton Chiles Ln | Tallahassee | FL | 32312 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA4505 | Company Owned | 2026-11-13 | 2026-11-21 | No Devices | 10/31/2025 | Not Delivered | Christian Fletcher | 1100 Roberts Rd | Calimesa | CA | 92320 | Sidney Krall | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0303 | Company Owned | 2026-11-15 | 2026-11-22 | No Devices | Not Shipped | Not Delivered | Isaac Schoephoerster | 1770 Pecan Ln | Kernersville | NC | 27284 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
UT0407 | Company Owned | 2026-11-10 | 2026-11-23 | No Devices | Not Shipped | Not Delivered | Mark Essey | 1121 South Jordan Pkwy | South Jordan | UT | 84095 | Christopher Triglia | Sun-Sat: 05am-11pm
FL2805 | Company Owned | 2026-11-17 | 2026-11-24 | No Devices | Not Shipped | Not Delivered | Nolan Owens | 10150 S US Hwy 441 | Belleview | FL | 34420 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL0506 | Company Owned | 2026-11-18 | 2026-11-24 | No Devices | Not Shipped | Not Delivered | Amber Webb | 5999 Northwest Hwy | Crystal Lake | IL | 60014 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0402 | Company Owned | 2026-11-18 | 2026-11-25 | No Devices | Not Shipped | Not Delivered | German Diaz Ramirez | 457 W North St | Springfield | OH | 45504 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA7301 | Company Owned | 2026-11-20 | 2026-11-27 | No Devices | Not Shipped | Not Delivered | Sydney Bighaus | 1819 N Tustin Avenue | Santa Ana | CA | 92705 | Jordan Gonsalves | Sun-Sat: 05am-11pm
SC0803 | Company Owned | 2026-11-18 | 2026-11-27 | Seal Verification | 05/26/2026 | 05/28/2026 | Charles Callen | 9430 Charlotte Hwy | Indian Land | SC | 29707 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL1704 | Company Owned | 2026-11-19 | 2026-11-28 | No Devices | Not Shipped | Not Delivered | Beau Beesley | 4959 US 90 | Pace | FL | 32571 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
GA1002 | Company Owned | 2026-11-20 | 2026-11-28 | No Devices | Not Shipped | Not Delivered | Joseph Caron | 3064 Washington Rd | Augusta | GA | 30907 | Stacy Wheeler | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
LA0303 | Company Owned | 2026-11-20 | 2026-11-28 | No Devices | Not Shipped | Not Delivered | Clark Gagne | 27392 Crossing Cir | Denham Springs | LA | 70726 | Jackson Luckin | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL2906 | Company Owned | 2026-11-18 | 2026-11-30 | No Devices | Not Shipped | Not Delivered | Jake Mottlow | 1604 Clearlake Rd | Cocoa | FL | 32922 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IN0805 | Company Owned | 2026-11-20 | 2026-11-30 | No Devices | Not Shipped | Not Delivered | Austin Hermanson | 4911 Illinois Road | Fort Wayne | IN | 46804 | Austin Winegar | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA6405 | Company Owned | 2026-11-24 | 2026-12-01 | No Devices | Not Shipped | Not Delivered | Juan Hernandez | 5809 Lakewood Blvd | Lakewood | CA | 90712 | Sidney Krall | Sun-Sat: 05am-11pm
IL0901 | Company Owned | 2026-11-24 | 2026-12-01 | No Devices | Not Shipped | Not Delivered | Delaney Joncek | 316 Madison St | Oak Park | IL | 60302 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TN0909 | Company Owned | 2026-11-25 | 2026-12-02 | No Devices | Not Shipped | Not Delivered | Destiny Musgrave | 3723 Ringgold Rd | East Ridge | TN | 37412 | JJ Herzog | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
UT0708 | Company Owned | 2026-11-23 | 2026-12-02 | No Devices | Not Shipped | Not Delivered | Blake Pratt | 2137 W Antelope Drive | Syracuse | UT | 84075 | Christopher Triglia | Sun-Sat: 05am-11pm
OH0403 | Company Owned | 2026-11-25 | 2026-12-04 | No Devices | Not Shipped | Not Delivered | German Diaz Ramirez | 2233 N Limestone St | Springfield | OH | 45503 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
VA0202 | Company Owned | 2026-11-25 | 2026-12-06 | No Devices | Not Shipped | Not Delivered | Wyatt Johnson | 5601 George Washington Hwy | Yorktown | VA | 23692 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TN1105 | Company Owned | 2026-11-30 | 2026-12-07 | No Devices | Not Shipped | Not Delivered | Cole Beeson, Anisa Gonzalez | 6206 Stage Rd | Bartlett | TN | 38134 | JJ Herzog | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
SC0501 | Company Owned | 2026-12-03 | 2026-12-10 | No Devices | Not Shipped | Not Delivered | Joseph Caron | 208 Edgefield Rd | North Augusta | SC | 29841 | Stacy Wheeler | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
GA0703 | Company Owned | 2026-12-04 | 2026-12-11 | No Devices | Not Shipped | Not Delivered | Christopher Redd | 3266 S Cobb Drive SE | Smyrna | GA | 30080 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0406 | Company Owned | 2026-12-04 | 2026-12-11 | No Devices | Not Shipped | Not Delivered | Mikayla Hulsing | 115 Woodman Drive | Riverside | OH | 45431 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA3711 | Company Owned | 2026-12-05 | 2026-12-12 | No Devices | Not Shipped | Not Delivered | Alyssa Hamer | 73270 Dinah Shore Dr | Palm Desert | CA | 92211 | Michael Coste | Sun-Sat: 05am-11pm
CO0608 | Company Owned | 2026-12-06 | 2026-12-13 | No Devices | Not Shipped | Not Delivered | Eli Copsey | 2245 Fremont Dr | Cañon City | CO | 81212 | Jarod Adducci | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
KS0405 | Company Owned | 2026-12-08 | 2026-12-15 | No Devices | Not Shipped | Not Delivered | Jacob Dub | 210 Tuttle Creek Blvd | Manhattan | KS | 66502 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0203 | Company Owned | 2026-12-08 | 2026-12-15 | No Devices | Not Shipped | Not Delivered | Hannah Gutt | 5635 Albemarle Rd | Charlotte | NC | 28212 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0502 | Company Owned | 2026-12-09 | 2026-12-16 | No Devices | Not Shipped | Not Delivered |  | 2860 W Alexanderville Bellbrook Rd | Dayton | OH | 45459 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TN0704 | Company Owned | 2026-12-10 | 2026-12-17 | No Devices | Not Shipped | Not Delivered | Christopher Flowers | 2219 E Morris Blvd | Morristown | TN | 37813 | JJ Herzog | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0107 | Company Owned | 2026-12-11 | 2026-12-18 | No Devices | Not Shipped | Not Delivered | Nate Garvin | 8221 Hwy 72 West | Madison | AL | 35758 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
GA0301 | Company Owned | 2026-12-11 | 2026-12-18 | No Devices | Not Shipped | Not Delivered | Camille Gibassier | 2515 Whittlesey Boulevard | Columbus | GA | 31909 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TN0908 | Company Owned | 2026-12-14 | 2026-12-21 | No Devices | Not Shipped | Not Delivered | Destiny Musgrave | 3395 Rhea County Hwy | Dayton | TN | 37321 | JJ Herzog | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA4309 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Toni Mestre | 540 Tucker Rd | Tehachapi | CA | 93561 | Kevin Harper | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IA0101 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Katie Lyons | 460 SE Alices Rd | Waukee | IA | 50263 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL0105 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Jessica Weber | 1672 Carlyle Ave | Belleville | IL | 62221 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL0501 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Amber Webb | 541 South Randall Rd | Algonquin | IL | 60102 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL1504 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Max Elwell | 6950 E Riverside Blvd | Loves Park | IL | 61111 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
KS0406 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Jacob Dub | 412 E. Chestnut | Junction City | KS | 66441 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
MO0502 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Alyssa Schultz | 100 Crossroads Plaza | O Fallon | MO | 63368 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0501 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Dakota Roeder | 210 Greenville Blvd SE | Greenville | NC | 27858 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0102 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Kaden Caldwell | 5208 Kings Mills Rd | Mason | OH | 45040 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0404 | Company Owned | 2026-12-15 | 2026-12-22 | No Devices | Not Shipped | Not Delivered | Mikayla Hulsing | 220 E Dayton Yellow Springs Rd | Fairborn | OH | 45324 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL1103 | Company Owned | 2026-12-16 | 2026-12-23 | No Devices | Not Shipped | Not Delivered | Whitney Nelson-Vasquez | 2211 75th Street | Darien | IL | 60561 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL0409 | Company Owned | 2026-12-18 | 2026-12-25 | No Devices | Not Shipped | Not Delivered | Meghan Sviontek | 3120 N Orange Blossom Trail | Kissimmee | FL | 34741 | Shawn McElroy | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0206 | Company Owned | 2026-12-18 | 2026-12-25 | No Devices | Not Shipped | Not Delivered | Matthew Forman | 1202 Main St | Hamilton | OH | 45013 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OK0414 | Company Owned | 2026-12-18 | 2026-12-27 | No Devices | Not Shipped | Not Delivered | Konstantin Paskar | 6701 S Memorial Dr | Tulsa | OK | 74133 | Jayson Jones
FL1305 | Company Owned | 2026-12-18 | 2026-12-29 | No Devices | Not Shipped | Not Delivered | Lucas Castanon | 5430 Beach Blvd | Jacksonville | FL | 32207 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL0603 | Company Owned | 2026-12-18 | 2026-12-30 | No Devices | Not Shipped | Not Delivered | Kolton Rohde | 16309 NW US HWY 441 | Alachua | FL | 32615 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IN0106 | Company Owned | 2026-12-24 | 2026-12-31 | No Devices | Not Shipped | Not Delivered | Ashlee Teeuwen | 1024 Commerce Drive | Franklin | IN | 46131 | Austin Winegar | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0604 | Company Owned | 2026-12-24 | 2026-12-31 | No Devices | Not Shipped | Not Delivered | Andre Kane | 9930 Johnstown Rd. | New Albany | OH | 43054 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0401 | Company Owned | 2026-12-25 | 2027-01-01 | No Devices | Not Shipped | Not Delivered | Julie Morgan | 521 Huffman Mill Rd | Burlington | NC | 27215 | Pattrick Gregson
TX6602 | Company Owned | 2026-12-30 | 2027-01-06 | No Devices | Not Shipped | Not Delivered | Blain Hobbs | 4717 Gollihar Rd | Corpus Christi | TX | 78411 | Erin Campbell
OH0605 | Company Owned | 2026-12-31 | 2027-01-07 | No Devices | Not Shipped | Not Delivered | Andre Kane | 5939 S Sunbury Rd | Westerville | OH | 43081 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0208 | Company Owned | 2027-01-01 | 2027-01-08 | No Devices | Not Shipped | Not Delivered | Hannah Gutt | 4045 Concord Pkwy S | Concord | NC | 28027 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL0804 | Company Owned | 2027-01-07 | 2027-01-13 | No Devices | Not Shipped | Not Delivered | Tyler Forman | 5784 Taylor Branch Road | Port Orange | FL | 32127 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
WA0102 | Company Owned | 2027-01-11 | 2027-01-18 | No Devices | Not Shipped | Not Delivered | Bree Frost | 2918 164th St SW | Lynnwood | WA | 98087 | Rennika Doty | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
GA0502 | Company Owned | 2027-01-08 | 2027-01-20 | No Devices | Not Shipped | Not Delivered | Maggie Briggs | 2345 N Columbia St | Milledgeville | GA | 31061 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IL0902 | Company Owned | 2027-01-14 | 2027-01-21 | No Devices | Not Shipped | Not Delivered | Nicholas Martinez | 4305 First Avenue | Lyons | IL | 60534 | Allie Lahti
OH0504 | Company Owned | 2027-01-14 | 2027-01-21 | No Devices | Not Shipped | Not Delivered |  | 301 Batsey Dr. | Middletown | OH | 45044 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL2701 | Company Owned | 2027-01-15 | 2027-01-22 | No Devices | Not Shipped | Not Delivered | Pac Dechasiri | 2050 S US Hwy 1 | Fort Pierce | FL | 34950 | Shawn McElroy | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0703 | Company Owned | 2027-01-19 | 2027-01-26 | No Devices | Not Shipped | Not Delivered | Anthony Macaskill-Haddock | 1205 AL-21 | Oxford | AL | 36203 | Michael Fameli
FL0103 | Company Owned | 2027-01-20 | 2027-01-27 | No Devices | Not Shipped | Not Delivered | Ardan Berg | 12230 Lake Underhill Rd | Orlando | FL | 32825 | Shawn McElroy | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
FL2904 | Company Owned | 2027-01-20 | 2027-01-27 | No Devices | Not Shipped | Not Delivered | Shania Mottlow | 4464 Hollywood Blvd | Melbourne | FL | 32904 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
TX4105 | Company Owned | 2027-01-20 | 2027-01-27 | No Devices | Not Shipped | Not Delivered | Christopher Reed | 19671 Gulf Freeway | Webster | TX | 77598 | Amanda Bigam
FL1804 | Company Owned | 2027-01-22 | 2027-01-29 | No Devices | Not Shipped | Not Delivered | Chelsey McElroy | 8604 Little Rd | New Port Richey | FL | 34654 | Chandell Nganga
WA1516 | Franchise | 2027-01-18 | 2027-01-29 | No Devices | Not Shipped | Not Delivered | Kerry Parker | 4501 S Regal St | Spokane | WA | 99223 | Nate Hartwig
SC0901 | Company Owned | 2027-01-22 | 2027-01-30 | No Devices | Not Shipped | Not Delivered | Jocelyn Adame | 1619 John B White Sr Blvd | Spartanburg | SC | 29301 | Stacy Wheeler | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0802 | Company Owned | 2027-01-29 | 2027-02-05 | No Devices | Not Shipped | Not Delivered | Gabe Filler | 4575 Hermitage Rd | Mobile | AL | 36619 | Michael Fameli
FL3104 | Company Owned | 2027-01-26 | 2027-02-05 | No Devices | Not Shipped | Not Delivered |  | 14430 FL-64 | Bradenton | FL | 34212 | Shawn McElroy
SC0201 | Company Owned | 2027-01-29 | 2027-02-05 | No Devices | Not Shipped | Not Delivered | Trevor Levanen | 5211 Sunset Blvd | Lexington | SC | 29072 | Stacy Wheeler
GA0504 | Company Owned | 2027-01-31 | 2027-02-07 | No Devices | Not Shipped | Not Delivered | Maggie Briggs | 860 SR 96 | Warner Robins | GA | 31088 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CO1205 | Company Owned | 2027-02-05 | 2027-02-12 | No Devices | Not Shipped | Not Delivered | Tyler Totten | 5858 S Aurora Parkway | Aurora | CO | 80016 | Jarod Adducci | Sun-Sat: 05am-11pm
CA3809 | Company Owned | 2027-02-06 | 2027-02-13 | No Devices | Not Shipped | Not Delivered | Jose Zamora-Saldana | 305 Woollomes Avenue | Delano | CA | 93215 | Kevin Harper
FL1306 | Company Owned | 2027-02-06 | 2027-02-13 | No Devices | Not Shipped | Not Delivered | Lucas Castanon | 2745 Charbray Dr | Jacksonville | FL | 32277 | Chandell Nganga | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
MS0202 | Company Owned | 2027-02-08 | 2027-02-15 | No Devices | Not Shipped | Not Delivered |  | 110 Strickland Dr | Flowood | MS | 39232 | Cory Nimmer
VA0303 | Company Owned | 2027-02-09 | 2027-02-18 | No Devices | Not Shipped | Not Delivered | Austin Ilonummi | 12027 Route 1 | Chester | VA | 23831 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
ID0506 | Company Owned | 2027-02-13 | 2027-02-20 | No Devices | Not Shipped | Not Delivered | Andrew Hollingsworth | 2708 S Lincoln Ave | Jerome | ID | 83338 | Rennika Doty
IL0701 | Company Owned | 2027-02-15 | 2027-02-22 | No Devices | Not Shipped | Not Delivered | Caleb Ball, Ryn Burt | 20900 LaGrange Rd | Frankfort | IL | 60423 | Allie Lahti | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA6106 | Company Owned | 2027-02-19 | 2027-02-26 | No Devices | Not Shipped | Not Delivered | Jorden Larson | 1411 N Hacienda Blvd | La Puente | CA | 91744 | Sidney Krall
SC0208 | Company Owned | 2027-02-18 | 2027-02-26 | No Devices | Not Shipped | Not Delivered | Trevor Levanen | 2245 Sunset Blvd | West Columbia | SC | 29169 | Stacy Wheeler
CA8106 | Company Owned | 2027-02-21 | 2027-02-28 | No Devices | Not Shipped | Not Delivered | Tyler Mcevoy | 850 N Wilcox Ave | Montebello | CA | 90640 | Sidney Krall
GA0707 | Company Owned | 2027-02-23 | 2027-03-02 | No Devices | Not Shipped | Not Delivered | Elexis Urena | 725 Whitlock Ave SW | Marietta | GA | 30064 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0203 | Company Owned | 2027-02-24 | 2027-03-03 | No Devices | Not Shipped | Not Delivered | Matthew Forman | 495 E Kemper Rd | Springdale | OH | 45246 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0803 | Company Owned | 2027-02-27 | 2027-03-06 | No Devices | Not Shipped | Not Delivered | Gabe Filler | 610 Schillinger Rd S | Mobile | AL | 36695 | Michael Fameli | Sun: 05am-10pm, Mon: 05am-10am, Tue-Thu: 05am-10pm, Fri-Sat: 05am-11pm
CA0916 | Company Owned | 2027-03-01 | 2027-03-08 | No Devices | Not Shipped | Not Delivered | Tatiana Lutz | 12840 Mono Way | Sonora | CA | 95370 | Matt Deacon | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
AL0702 | Company Owned | 2027-03-05 | 2027-03-12 | No Devices | Not Shipped | Not Delivered | Karl Cosajay | 1859 Montgomery Hwy | Hoover | AL | 35244 | Michael Fameli | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
MO0305 | Company Owned | 2027-03-05 | 2027-03-12 | No Devices | Not Shipped | Not Delivered | Stephanie Cotton | 4690 Osage Beach Pkwy | Osage Beach | MO | 65065 | Tyler Smith | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
NC0601 | Company Owned | 2027-03-05 | 2027-03-12 | No Devices | Not Shipped | Not Delivered | Logan Cothran | 7585 S Raeford Rd | Fayetteville | NC | 28304 | Pattrick Gregson | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
OH0603 | Company Owned | 2027-03-17 | 2027-03-24 | No Devices | Not Shipped | Not Delivered |  | 802 N Memorial Dr | Lancaster | OH | 43130 | Taylor Jacobs | Sun-Thu: 05am-10pm, Fri-Sat: 05am-11pm
IN1001 | Company Owned | 2027-03-31 | 2027-04-07 | No Devices | Not Shipped | Not Delivered | Dakota Hess | 13000 Adams Road | Granger | IN | 46530 | Austin Winegar